## Sheet1
ID | Story Pts | Sprint Backlog | Tasks | Status | Owner | Orig | Done | Remain
0 | 11 | Encompassing | Study XAMPP & CodeIgniter | DONE | JM | 2 | 2 | 0
|  |  | Install XAMPP & CodeIgniter | DONE | JM | 1 | 1 | 0
|  |  | Requirements model - Class Diagram | DONE | JM | 2 | 2 | 0
|  |  | Component design - Elaborated Class Diagram | On Going | JM | 2 | 1 | 1
|  |  | Create and execute SQL script to populate missing transaction numbers | To Be Done | JM | 1 | 0 | 1
|  |  | Translate all old MySQL Query commands into POSTGRES | To Be Done | JM | 3 | 0 | 3
1 | 5 | Faculty Application Request [Create a study leave form, Evaluate requests using RSO calculator] | Design Back | On Going | JM | 1 | 0.5 | 0.5
|  |  | Code Back | To Be Done | JM | 3 | 0 | 3
|  |  | Merge Front Back | To Be Done | JM | 1 | 0 | 1
3 | 7 | Faculty AND ADMIN notification [Display notifications on the Faculty Homepage] | Design Back | On Going | JM | 2 | 0.5 | 1.5
|  |  | Code Back | To Be Done | JM | 3 | 0 | 3
|  |  | Merge Front Back | To Be Done | JM | 2 | 0 | 2
8 | 7 | Admin Faculty List [Display list of faculty, Edit details of faculty, Delete a faculty, Create a new faculty, Filter list, Sort alphabetically, Quick search, Advanced search, Color coded according to RSO stat] | Design Back | Done | JM | 1 | 1 | 0
|  |  | Code Back | On Going | JM | 5 | 2 | 3
|  |  | Merge Front Back | To Be Done | JM | 1 | 0 | 1
9 | 6 | Admin Transaction [Display list of faculty transactions, Filter list, Sort list by: date, transaction#, Quick Search, Advanced search Color code according to RSO stat] | Design Back | Done | JM | 2 | 2 | 0
|  |  | Code Back | On Going | JM | 3 | 2 | 1
|  |  | Merge Front Back | To Be Done | JM | 1 | 0 | 1
GROSS | 36 |  |  |  | STATUS | 36 | 14 | 22
CORE | 25 |  |  |  | CORE | 25 | 8 | 17